## Sheet1
People in-charge
|  | 2024 | [7 empty] | 2025 | [11 empty] | 2026
|  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Field | Piloting | [22 empty] | SH, SK, SI, YH
| Recruitment | [22 empty] | SH, SK, SI
Training
Pregnant mother surveillance
Child enrolment
Child sample collection
Child follow-up
PBMC isolation | Optimize PBMC freezing | [22 empty] | DPK, ARM, YH | bar: 2024 May to 2024 Jun
Do PBMC isolation trials | bar: 2024 Jun to 2024 Nov
PBMC isolation | bar: 2024 Nov to 2025 Dec
ELISA testing | Procure ELISA reagents | [22 empty] | ARM, AS | bar: 2024 May to 2024 Oct
ELISA test optimization | bar: 2024 Oct to 2024 Dec
ELISA testing of samples | bar: 2024 Dec to 2026 Jan
scRNAseq | Shipments | [22 empty] | MHK | bar: 2024 May to 2024 Sep; 2024 Nov to 2025 Mar
| Cartridge procurement | [22 empty] | AMT, DPK, ARM | bar: 2024 May to 2024 Aug; 2024 Nov to 2025 Mar
scRNA runs | bar: 2024 Sep to 2024 Oct; 2025 Apr to 2025 Jun; 2025 Dec to 2026 Feb
Data analysis | bar: 2024 Sep to 2024 Nov; 2025 Apr to 2025 Sep; 2025 Dec to 2026 Feb
Shalek lab visit | bar: 2024 Dec to 2025 Jan
| SH | 2024 May: Shameem Hassan
| SK | 2024 May: Sakiul Kabir
| SI | 2024 May: Shahidul Islam
| YH | 2024 May: Yogesh Hooda
| ARM | 2024 May: Apurba Rajib Malaker
| AMT | 2024 May: Arif M Tanmoy
| DPK | 2024 May: Deb Purna Keya
| MHK | 2024 May: Monimul Hasan Khan